## Day9
Participants | Test Case / Story Id | Test Case Complexity | Progress in 60 mins | Progress in 120 mins | Progress in 180 mins | Progress in 240 mins | Comments /Feedback | Action Items
GOMATHI J | Create New Cases - Parameters, DP | Simple |  |  | Parameters, DP completed | Excel Reading in-progress
HARIPRIYA P | Create New Refund - Parameters, DP | Simple |  |  | Parameters, DP completed | Excel Reading in-progress
KRISHNAPRAKASH JEYARAM | Create Account - Parameters, DP | Simple |  |  | Parameters, DP completed | Excel Reading in-progress
SARANRAJ K | Leads Scenario - Parameters, DP | Simple |  |  | Parameters, DP completed | Excel Reading in-progress
SARANYA S | Create Task - Parameters, DP | Simple |  |  | Parameters, DP completed | Excel Reading in-progress
SEEETHALAKSHMI | Create WorkType - Parameters, DP | Simple |  |  | Parameters, DP completed | Excel Reading in-progress
SREE POORANI B | Absent | Simple
SRIDHAR | Crate New Oppurtunity - Parameters, DP | Simple |  |  | Parameters completed | DP in-progress | When compare to others he is little bit slow in coding speed. | Informed him to connect with team for any help